## Sheet1
Project | Sub-project | Leads | Design Doc Draft | Team Comments Processed | Public Comments Processed | Initial Implementation | In Reference App | RC0
Dependency Injection |  | Vojta, Brian | https://docs.google.com/document/d/1fTR4TcTGbmExa5w2SRNAkM1fsB9kYeOvfuiI99FgR24/edit#heading=h.2e8op9ntdrm0 | done | done | https://github.com/angular/di.js
Change detection |  | Misko, Igor, Caitlin | https://docs.google.com/document/d/10W46qDNO8Dl0Uye3QX0oUDPYAwaPl0qNy73TVLjd1WI | done | done | https://github.com/angular/watchtower.js
Templating |  | Tobias, Igor, Misko | https://docs.google.com/document/d/1f5VWROeTI2kJwVKbNsrHuEz5IqtZe14OpoxM9fEYJNU/edit# | 2014-02-25 | 2014-02-28 | https://github.com/angular/templating
Persistence | All | Jeff, Brian, Chirayu | https://docs.google.com/a/google.com/document/d/1DMacL7iwjSMPP0ytZfugpU4v0PWUK0BT6lhyaVEmlBQ/edit?usp=drive_web | done | done
| > ngHTTP | Jeff |  |  |  | 2014-03-17
| > ngWebSocket | Jeff |  |  |  | Angular 1.x module in-development: https://github.com/jeffbcross/ngSocket
| > ngStore | Jeff |  |  |  | 2014-03-28
| > ngOffline | Jeff |  |  |  | 2014-04-11
| > ngData | Jeff |  |  |  | ...
| > Promise | Jeff
Routing |  | Brian, Matias | https://docs.google.com/a/google.com/document/d/1I3UC0RrgCh9CKrLxeE4sxwmNSBl3oSXQGt9g3KZnTJI/edit?usp=docslist_api | 2014-02-21 | 2014-02-28 | https://github.com/angular/router
Logging |  | Merrick, Igor | https://docs.google.com/document/d/1gGUEODxxDjY7azF8InqtN1pRcLo3WhGb8BcoIihyI80/edit | 2014-02-24 | 2014-02-28 | https://github.com/angular/diary.js
RTT & Annotations |  | Vojta | https://docs.google.com/document/d/1u2cBiLV2aCXnAwXJOPghtxWoikH9hY6enUI1AE4k4cw/edit?usp=sharing | done
Documentation infrastructure for apps |  | Pete, Matias | https://docs.google.com/document/d/1RgWk3ludcL0k8Z59KoTXuMIgJsE6XjvO5WVI6obY5Xs/edit?usp=sharing
Benchmarking |  | James, "Jeff" | https://docs.google.com/document/d/1pHMbpInJtiMF2zp4AZaW2jYSkVvNQZLLYrqXhJRi2T8/edit | 2014-02-03 | 2014-03-07 | http://jbdeboer.github.io/todobenchmark?show
Touch/Animations |  | Tobias | https://docs.google.com/a/google.com/document/d/16Z6Lun15DoWNrE2imk7N-2WiRAaqc954LOfU2-2JSoI/edit# | 2014-02-28 | 2014-03-07 | 2014-02-21
Package repository |  | Igor, Pete or Pawel | https://docs.google.com/document/d/14t1u5bjJV0TDJxNHhJnZe6Qu8Tn0muWytwjfuVPdAdY/edit# | done | 2014-02-28
Reference App |  | Jeff, Igor | https://projects.angularjs.org | 2014-02-24
Scaffolding |  | ??? |  |  |  | Community has been having a go at this, apparently for NG2.0... https://github.com/glassvision/obtuse
Build |  | ???
Deploy |  | ???