## Sheet1
Priority: 1=blocks next release; 2=work focus; 3=nice to have; 4=background; 5=do not work on
Area | Description | Priority | Owner | Github Link | Action | Notes
Migration Helpers
| `module.component(...)` Syntactic Sugar | 1 | Pete | https://github.com/angular/angular.js/issues/10007 | Implement
| Angular 1 ES6/TypeScript Story | 1 | Pete |  | Coordinate | There is a team of external developers working on this Pete to get in touch
| Interoperability between v1 and v2 | 1 | Igor/Misko |  | Investigate | What would this mean? Two apps running side by side that have guarded interaction points Each is responsible for different route Igor is keeping on top of this - it will be ready by Angular 2 release
| Template syntax sugar | 5 |  |  | Too likely to cause confusion | Allow ng2 syntax
| Angular 2 DI | 1 | Lucas |  | Investigate V2 DI into V1 | There are problems implementing this. It is possible but it is tough.
| Migration tools | 1 |  |  | Investigate / write tools to migrate templates / other elements | Yet another strategy....
Router
| Building the router | 1 | Shahar | https://github.com/angular/angular/pull/3698 |  | TypeScript to wrapped Angular 1, taking into account DI
| Implementing Angular 1 bits | 1 | Shahar | https://github.com/angular/angular/pull/3698
i18n
| extraction of messages from templates + localized template generation | 2 | Pawel :-)
Core Changes
| Lazy Loading Components | 1 |  | https://github.com/angular/angular.js/issues/11015 | Investigate V2 DI into V1 | Related to ComponentRouter
| Support non-string identifiers for injection | 3
| Multi-transclusion | 1 | Pete | https://github.com/angular/angular.js/pull/12742 |  | Spiked a new API
| stricter injector | 3 |  |  |  | (Dependent upon lazy loading) If module Main module depends on A and B, and A does not depend on B, then if a service in A depends on B throw an error
| compile performance | 3 |  |  |  | Ideas: 1/ cache a compiled template 2/ precompute where the directives are and use this information instead of traversing the DOM
| Don't throw errors on bootup | 3 |  | https://github.com/angular/angular.js/issues/1248
| namespaced one-time binding | 5 |  |  |  | :namespace:expression | listens on the event `namespace` and restores the watcher. **namespace** is not an expression
| Make $compile(html)(scope) return a promise | 5 |  |  |  | Why? What does the promise represent?
| Better API for module redefinitions | 2 | Igor | https://github.com/angular/angular.js/issues/1779
New Directives
| File Upload Directive | 4 |  |  |  | Possible community driven project?
Backend Communication
| XHR Progress events | 3 | Pawel | https://github.com/angular/angular.js/issues/1934 |  | Very much requested and very much missing :-)
| AngularData | 4 |  |  |  | Replacement for $resource Related project: http://jsonapi.org/
| $http Url Building | 3 | Pawel | https://github.com/angular/angular.js/pull/3213
| $sce handling | 3 |  | https://github.com/angular/angular.js/issues/11328
| deprecate `success()` and `error()` methods | 2 | Pete | https://github.com/angular/angular.js/pull/12112
| improve caching API | 2 | Martin | https://github.com/angular/angular.js/issues/10961, https://github.com/angular/angular.js/issues/11101
Forms Improvements
| Handle watching complex model objects | 2 | Martin | https://github.com/angular/angular.js/issues/5449
| Improved <select> without ngOptions | 2 | Matias |  |  | If we can improve dynamic <options> then we could deprecate ngOptions
| Trigger formatters programmatically | 3 |  | https://github.com/angular/angular.js/pull/10764
| Inheritable ngModelOptions | 3 |  | https://github.com/angular/angular.js/pull/10922
| Support isolating nested forms | 3 |  | https://github.com/angular/angular.js/pull/10193
| Customizable model update conditions | 2 | Martin | https://github.com/angular/angular.js/issues/10035
| Hook into the input-change | 3 |  | https://github.com/angular/angular.js/issues/11634
| Metadata for / Structured validation errors | 3 | Martin | https://github.com/angular/angular.js/issues/11671
| Rework the parser error API | 2 | Martin | https://github.com/angular/angular.js/issues/10230
Miscellaneous
| Improved logging | 5 |  |  |  | There was a project called diary.js
| ngSwitchWhenSeparator | 3 |  | https://github.com/angular/angular.js/pull/10798
| Overriding directives | 3 |  | https://github.com/angular/angular.js/issues/11137 |  | This is tricky to do declaratively, perhaps a directive registration manipulation API would give better control?
| px attribute handling | 3 |  | https://github.com/angular/angular.js/issues/11626 |  | Has impact on ngAnimate
| $q.any ($q.race) | 5 |  | https://github.com/angular/angular.js/issues/11808 | Use decorator
| $time service | 4 |  | https://github.com/angular/angular.js/issues/10402
| allOrNothing on ngHref | 3 |  | https://github.com/angular/angular.js/issues/10015
| $prev and $next properties for ngRepeat | 4 |  | https://github.com/angular/angular.js/pull/9795
| ngTouch needs love or deprecation | 4 |  | Many open issues. Problem: testing | Deprecate -> Hammer, Fastclick, Ionic
$location related
| Remove non-html5 mode | 5 |  | https://github.com/angular/angular.js/issues/11451 |  | Would need to drop IE9 support. Why? What is the motivation here? The only proposal was to mark HTML5 mode as default: https://github.com/angular/angular.js/issues/11451
| ngAppRoot | 3 |  | https://github.com/angular/angular.js/issues/3102
| JQLite custom element support | 3 |  | https://github.com/angular/angular.js/pull/10619
| Allow URL changes without state change | 4 |  | https://github.com/angular/angular.js/issues/1699
Animation
| ngStyle compatibility | 2 | Matias | https://github.com/angular/angular.js/issues/10281
| new JS API | 2 | Matias

## Top issues
Issue | Area | What is all about? | Comments | Possible Action | Owner | Priority | 1.5 Action
https://github.com/angular/angular.js/issues/1699 | $location | Changing $location component without triggering routing | Probably don't want to do. | Understand the use-case and open other issues, if any | Brian | 3 | Investigate for 1.5
https://github.com/angular/angular.js/issues/1934 | $http | Adding support for progress events | Should do | There are open PRs: review / merge | Pawel | 2 | 1.5
https://github.com/angular/angular.js/issues/9128 | ? | Things failing on iOS, we can't reproduce | There is no reproduce... | ? |  |  | Close and ask for reproduction
https://github.com/angular/angular.js/issues/10007 |  | angular.component helper | Captured in the list of other tasks | Work on in 1.5 timeframe |  | 1 | 1.5
https://github.com/angular/angular.js/issues/11015 | $injector | Deferred loading of providers into the injector | Part of child injectors? | Work on in 1.5 timeframe | Brian? | 1 | 1.5
https://github.com/angular/angular.js/issues/528 | directives | Support HTML5 contentEditable attribute | User-land? | Close, explain that it should be a 3rd party component | Martin |  | Close - maybe get ngModel to play nicer
https://github.com/angular/angular.js/issues/5410 | $injector | Out of the Box Support for AMD | Do we care about AMD any-more? | Close and work on ES6/TS modules instead? |  |  | Close
https://github.com/angular/angular.js/issues/5489 | $compile | ng-transclude should not create new sibling scope | Why not... Configurable? What about nested transcludes? Footgun? | Tackle as part of multi-transclusion? | Pete / Igor | 4 | Investigate for 1.5
https://github.com/angular/angular.js/issues/1779 | $injector | Creating a module twice fails silently | We should fix it! | Work on in 1.5 timeframe | Igor | 3 | 1.5
https://github.com/angular/angular.js/issues/6251 | ngTouch | ngClick using ngTouch fires twice | What are the plans for ngTouch? | Elect an owner / find a contributtor? |  |  | Deprecate and suggest people use Hammer.js / ionic / etc
https://github.com/angular/angular.js/issues/5854 | $injector | support for ordered initialization of an angular app with asynchronous data | part of the async modules story? should be handled by a hook in a top level route of the new component router | Work on in 1.5 timeframe | Igor |  | Close
https://github.com/angular/angular.js/issues/4357 | ngMock | Allow multiple transcluding directives on an element | Already captured | Work on in 1.5 timeframe if we want to do multi-transclusion | Pete / Kara | 2 | 1.5
https://github.com/angular/angular.js/issues/1434 |  | $httpBackend "passThrough()" doesn't work | People want to do $http requests during tests | Close, explaining that we don't want to promote this | Pawel |  | check and close
https://github.com/angular/angular.js/issues/5892 | directives (input) | support for the input type=range | Why not? | Make range map to number input | Martin |  | 1.5
https://github.com/angular/angular.js/issues/1388 | ngResource | encoding of URI params | Need to understand the root of the pb | Investigate / work on in 1.5 timeframe? | Pawel | 3
https://github.com/angular/angular.js/issues/2548 | ngTouch |  |  | Elect an owner / find a contributtor? |  |  | See line 11
https://github.com/angular/angular.js/issues/2104 |  | Server-side rendering | Are we ever going to do it in ng1? | Close without upsetting people? | Igor |  | Close
https://github.com/angular/angular.js/issues/2767 | $injector | name collisions in $injector | So, how about child injectors? Won't work for directives, though |  | Lucas |  | Close unless we decide to go with A2 DI
https://github.com/angular/angular.js/issues/6039 | $http | Serializing body for x-www-form-urlencoded requests | Trivial to do now | Work on in 1.5 timeframe? | Pawel | 3 | 1.5
https://github.com/angular/angular.js/issues/2895 | $compile | People want to use ngInclude as poor-mans directive? | We don't wnat to go this way | Close, explaining reasons | Peter / Igor? |  | Close
https://github.com/angular/angular.js/issues/4003 | $injector | Async module-run | Duplicate of https://github.com/angular/angular.js/issues/5854 | Close of the issues as a duplicate | Igor |  | Close (see line 12)
https://github.com/angular/angular.js/issues/5146 | ngResource/$http | Specifing interceptors per-action | Do we want to do this? | Investigate / close | Pawel? | 4 | Investigate for 1.
https://github.com/angular/angular.js/issues/6354 | $scope | Bind-once namespacing | Do we want to do this? | Close? | Igor |  | close
https://github.com/angular/angular.js/issues/1102 | $location | One of the $location reload bugs | Might have been fixed? | Confirm / close? | Peter | 3 | Check if fixed