## Sheet1
Angular 1.4 - Primary Task Tracker
Area | Owner | Description | Discussion | Status
Router | Brian | Support asynchronous module.run() | #4003
I18N | Chirayu
$injector | Lucas | Creating a module twice fails silently | #1779
$parse | Lucas | `$eval` assignment expression and locals | #4664 | landed today
$parse | Lucas | $parse performance improvement refactoring |  | waiting for review
Forms | Martin/Pete | ngModelController: trigger change when only property of model changes | #5449 | Create Design Doc
|  | Bug: $asyncValidators destroys data bound model property | #10035
|  | Input[type=email] is not reset on model reset | #10027
|  | $validators should reset model to undefined upon invalid initial value | #10286
|  | number input filter is not working if we clear the value | #10230
|  | ngModel parse errors always use named parser | #10076
|  | Input group [Radio] validation fails | #10043
|  | support nested forms isolated from parent | #10193
ngRepeat | Rody | add $prev and $next properties to ngRepeat | #9795
HTTP | Pawel | $http always transform response content '[abc}' to JSON even we already set resp content type as 'application/octet-stream' | #10357
|  | Passing a string that contains a semi-colon doesn't properly get encoded | #9224
|  | $http refactoring (more configuration control - per domain, serialization, etc) |  | ARRANGE MEETING
Improve $http mocking DSL
$compile | Caitlin | throw when non-optional '&' binding is used but not specified | #9216 | Igor to review
$compile | Igor | module.component helper | #10007 | Look at next week (19/1/15)
ngAnimate | Matias | ngAnimate applying transition style to element causes undesirable | #10281
Project | Pete | split parts of core angular.js into modules |  | ARRANGE MEETING
limitToFilter | Pawel | limitTo filter improvements | #5355
ngPanel/ngPage | Matias | new widget to animate DOM elements when an expression changes
ngMessages | Matias | enable data driven message - say loaded from a server |  | PR waiting / Martin / Shahar
ngCookies | Shahar |  | #10530 | Igor reviewing